## Bug Report
Field | Details
Project Name | Sauce Demo Manual Testing Project
Application Under Test | SauceDemo (https://www.saucedemo.com)
Prepared By | Rohit Chaurasia
Role | Fresher QA Tester
Testing Type | Manual Testing
Reference Document | Sauce_Demo_Test-Cases.xlsx
Tools Used | Excel, Jira
Browser Used | Google Chrome
Test Cycle Dates | 08-Jul-2026 to 09-Jul-2026
Bug ID | Module | Test Case ID | Bug Title | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Environment | Date Reported
SD_BUG_001 | Login / Products | Login_TC_3 | Product images identical/incorrect for problem_user | 1. Login with problem_user / secret_sauce 2. Navigate to the Products page 3. Observe the image displayed for each product | Each product should display its own correct, corresponding image | All products display the same incorrect image instead of their actual product image | Major | High | Open | Google Chrome (Latest), Windows 10 | 08-Jul-2026
SD_BUG_002 | Products | Products_TC_5 | Sorting by Name (Z to A) does not reorder products for problem_user | 1. Login with problem_user / secret_sauce 2. Open the sort dropdown on Products page 3. Select "Name (Z to A)" option | Products should reorder into descending alphabetical order by name | Product order does not change after selecting the sort option; sort appears broken | Major | Medium | Open | Google Chrome (Latest), Windows 10 | 08-Jul-2026
SD_BUG_003 | Product Details | ProductDetail_TC_2 | "Add to cart" button unresponsive on select Product Details pages for problem_user | 1. Login with problem_user / secret_sauce 2. Open a Product Details page (e.g. Sauce Labs Bolt T-Shirt) 3. Click the "Add to cart" button | Product should be added to cart and button should change to "Remove" | Button does not respond on click; item is not added to cart and badge count stays unchanged | Critical | High | Open | Google Chrome (Latest), Windows 10 | 08-Jul-2026
SD_BUG_004 | Checkout | Checkout_TC_3 | Last Name field overwrites First Name field during checkout for error_user | 1. Login with error_user / secret_sauce 2. Add any item to cart and proceed to Checkout Information page 3. Enter a value in the First Name field 4. Enter a value in the Last Name field | First Name and Last Name should be captured independently in their respective fields | Typing in the Last Name field overwrites the First Name field content; only a single character can be retained | Critical | High | Open | Google Chrome (Latest), Windows 10 | 08-Jul-2026
SD_BUG_005 | Checkout | Checkout_TC_1 | Zip/Postal Code field accepts non-numeric and special characters | 1. Open Checkout Information page 2. Enter valid First Name and Last Name 3. Enter a non-numeric value in the Zip Code field (e.g. "abc@#") 4. Click Continue button | System should validate the Zip/Postal Code format and reject non-numeric input | System accepts any character type in the Zip Code field and proceeds to the Checkout Overview page | Minor | Low | Open | Google Chrome (Latest), Windows 10 | 09-Jul-2026
SD_BUG_006 | Menu / Navigation | Menu_TC_7 | Products page briefly accessible via browser Back button after logout | 1. Login with standard_user / secret_sauce 2. Logout using the burger menu 3. Click the browser Back button | User should remain on the Login page; Products page should not be accessible after logout | A cached version of the Products page is briefly displayed via browser back navigation | Minor | Medium | Open | Google Chrome (Latest), Windows 10 | 09-Jul-2026
SD_BUG_007 | Products | Products_TC_9 | Cart icon renders oversized/misaligned for visual_user after adding items | 1. Login with visual_user / secret_sauce 2. Add any product to cart 3. Observe the cart icon in the top-right corner | Cart icon should remain correctly sized and aligned with the header | Cart icon renders oversized and visually misaligned compared to the standard layout | Minor | Low | Open | Google Chrome (Latest), Windows 10 | 09-Jul-2026
SD_BUG_008 | Login | Login_TC_4 | Noticeable delay (~5-7 seconds) after login for performance_glitch_user | 1. Enter performance_glitch_user credentials 2. Click Login button 3. Observe time taken to load the Products page | Page should load within an acceptable response time | Products page takes approximately 5-7 seconds to load, significantly slower than standard_user | Minor | Low | Rejected – By Design | Google Chrome (Latest), Windows 10 | 08-Jul-2026
SD_BUG_009 | Product Details | ProductDetail_TC_1 | Invalid product ID accessible via direct URL and addable to cart | 1. Login with any valid user 2. Navigate directly to a Product Details URL with a non-existent product ID 3. Observe the page content 4. Click "Add to cart" if available | System should display a proper "Product not found" message for invalid product IDs | Page loads without valid product details, yet the "Add to cart" action is still accepted | Minor | Low | Open | Google Chrome (Latest), Windows 10 | 09-Jul-2026
SD_BUG_010 | Cart | Cart_TC_3 | "Remove" button state does not update immediately on Cart page for error_user | 1. Login with error_user / secret_sauce 2. Add a product to cart 3. Open the Cart page 4. Click the "Remove" button on the item | Item should be removed from the cart and the row/button should disappear immediately | Item is removed from the cart count, but the row and button remain visible until the page is refreshed | Minor | Medium | Open | Google Chrome (Latest), Windows 10 | 09-Jul-2026
SD_BUG_011 | Checkout | Checkout_TC_12 | Order can be completed via Checkout Overview with an empty cart | 1. Login with standard_user / secret_sauce 2. Ensure cart is empty (remove all items) 3. Navigate directly to the Checkout Overview page 4. Click "Finish" button | System should prevent order completion when the cart contains no items | Order completes successfully with an empty cart and the confirmation message is displayed | Major | Medium | Open | Google Chrome (Latest), Windows 10 | 09-Jul-2026
SD_BUG_012 | Menu / Navigation | Menu_TC_5 | Cart page does not immediately reflect "Reset App State" without navigation | 1. Add multiple items to cart 2. Open the Cart page 3. Open burger menu and click "Reset App State" 4. Observe the Cart page without navigating away | Cart page should immediately reflect the reset state and show no items | Cart page continues to display previously added items until the page is manually refreshed or revisited | Minor | Low | Open | Google Chrome (Latest), Windows 10 | 09-Jul-2026
SD_BUG_013 | Footer | Footer_TC_1 | Footer social media links do not navigate to valid Sauce Labs pages | 1. Login with standard_user / secret_sauce 2. Scroll to the footer 3. Click the Twitter/X icon 4. Observe the destination page | Link should open the official Sauce Labs social media page in a new tab | Link opens a generic or broken destination instead of a valid, current Sauce Labs social page | Minor | Low | Open | Google Chrome (Latest), Windows 10 | 09-Jul-2026
SD_BUG_014 | Checkout | Checkout_TC_8 | Tax value occasionally displayed with inconsistent decimal rounding | 1. Add multiple items with decimal prices to cart 2. Proceed to the Checkout Overview page 3. Observe the Tax and Total values | Tax should be calculated and displayed with consistent 2-decimal rounding | Tax value occasionally displays with rounding inconsistent with the Total shown | Minor | Low | Open | Google Chrome (Latest), Windows 10 | 09-Jul-2026
Severity / Priority Legend
Critical | Blocks core functionality; no workaround available (e.g. cannot complete checkout)
Major | Significantly impacts functionality; workaround may exist
Minor | Small functional or cosmetic issue; low impact on usage
High Priority | Should be fixed before next release
Medium Priority | Should be fixed in upcoming releases
Low Priority | Can be fixed when convenient; low business impact